## Cover
General Information
Project ID | SAUCE_01
Client | Saucedemo
Author(s) | Suhashini Gajbhiye
Creation Date | 2023-02-15
Modification Date | 2023-02-20
Privacy Information
It contains information of a sensitive nature. This information should not be given to persons other than those who are involved with this project or who will become involved during its lifecycle.
Change Control
Revision Date |  | Author | Section(s) | Summary
2023-02-20 |  | Vishal Vishnu Patil | Overall Status | Changes done in the pass percentage of the defects

## STATUS REPORT
Overall progress of the QA cycle(on time/delayed/stopped) | On time
Total number of test cases | 88
Number of testers | 1
Test cycle duration (in days) | 30
Status of <Date>
Number of test cases planned | 100
Number of test cases executed | 88
Number of test cases executed overall | 88
Number of defects encountered today | 4
Number of defect encountered so far | 34
Number of critical defects- still open | 4
Overall Status
Number of test cases planned | 100
Number of test cases executed | 88
Pass Percentage of the defects | 0.61
Defects density (per day) | 0.98
Critical defects percentage | 0.2